## Sheet1
[7 empty] | Key: | Completed schemes
Cancelled schemes
REF | Scheme Name | Scheme Stage | Finish | CMA approved | Cost Code | Scheme Category | Works Description | Allocated Budget | Comments
Approved Schemes- 2018/19 Delivery - Safer Road Schemes
1 | First Avenue jw Orchard Croft | Design | Quarter 3 |  | LHAR181001 | Safer Roads | Design to look at: - Bus lane length reduction - New traffic island - Right turn lane | 7500 | Casualty reduction scheme.
Approved Schemes - Prioritised for 2018/19
2 | Tawneys Road on the approach to William Martin School - Advisory 20mph | Total scheme | COMPLETED |  | LHAR172003 | Traffic Management | Advisory 20mph limit on the approach to the school following on from feasibility study undertaken in 2016-17 | 12000
3 | Parsloe Road junction with Phelips Road and Markwell Wood - Traffic management | Implementation | COMPLETED | 2016-04-12 08:00 | LHAR162001 | Traffic Management | Implementation of scheme to provide deflection for roundabout following on from feasibility study undertaken in 2015-16 | 82500
4 | Hamstel Road - Parallell / Tiger crossing | Implementation | 2019-20 |  | LHAR173002 | Walking | Implementation of tiger crossing in the vicinity of the hospital | 62500 | Members agreed to defer the installation of the crossing to early into the 2019-20 financial year. The final costs are awaited as will now incorporate UKPN costs and elements which differed from the original zebra crossing commission.
5 | Fourth Avenue junction with North Gate - Roundabout works | Total scheme | 2019-04-01 |  | LHAR162009 | Traffic Management | Implementation of works as identified in the feasibility study undertaken in 2017-18 to look at redesigning the roundabout | 66500 | The installation date has been provisionally booked in for the 23rd April.
6 | Pottersfield - Congestion parking | Implementation | Quarter 4 |  | LHAR172004 | Traffic Management | Installation of the Pottersfield parking works as designed in 2017-18 | 87000 | The installation works commenced on 11th March and will be completed before the end of the financial year instead of being split over two years.
7 | Church End - Pram crossing | Total scheme | Quarter 4 |  | LHAR173003 | Walking | Design and installation of pram crossing | 2000
8 | Woodcroft - Pram crossing | Total scheme | Quarter 4 |  | LHAR173006 | Walking | Design and installation of pram crossing | 2000
Approved Schemes - Prioritised for 2019/20
9 | Tawneys Road close to the shops - Zebra crossing | Feasibility | 2019/20 |  | LHAR173005 | Walking | Design and TRO for new zebra crossing | 8500 | Members provisionally agreed the funding at the January Panel meeting subject to Cabinet Member approval